## Issue Tracking
| PowerPic Bugtracking | 2014-02-25
No. | Category | Build Version | Item | Description | Current Owner | Status | Comments | Related to
1 | Bugs | 2013-12-29 | Crashes when adding folders with sub folders (win7 64bit, German) |  | Jawahar | Working / Investigating | Could partially be solved by turning off UAC (new user account, empty database). In my admin account the application is still not usable, the database cant be reset even though UAC is turned off.
2 | Bugs | 29.12.2013 20.01.2014 | Crashes often while using the search function. When search doesn't crash, search results are not readable | Search results don't relate to the contents of the database. The empty database can also be searched and will return "20" | Jawahar | Closed | Searches without results still return "20"
3 | Other | 2013-12-29 | In general very unstable but that's probably due to the early maturity of the application | Maybe increase logging for development versions to better investigate? | Jawahar | Working / Investigating
4 | Performance Improvements | 2013-12-29 | Adding a folder causes a delay until the folder is appearing in the main window | Can the performance be improved? | Jawahar | Closed | Progress shown.
5 | Usability and UI | 2013-12-29 | Please add a progress bar or something similar when images are added so the app doesnt "freeze" |  | Jawahar | Closed | Progress and status shown. mr: looks great! | 4
6 | Performance Improvements | 2013-12-29 | Full view/zooming into an image is very slow. Double clicking doesn't cause an immediate reaction | This only applies to large files. We should think about adding a second "preview" (1024x768) to the database. Many large photos will have ~24MP that can't be displayed in full anyways | Jawahar | Closed | Optimized the navigation.
7 | Performance Improvements | 2013-12-29 | Returning from full view/zoom isn't "smooth" but stutters |  | Jawahar | Closed | Fixed.
8 | Usability and UI | 2013-12-29 | Add "Escape" keyboard shortcut to return from full view to browse view |  | Jawahar | Closed | mr: has been implemented, thanks!
9 | General Improvements | 2013-12-29 | Window for "browse folders" is not centered; needs to be moved manually because the buttons are beyond the visible area | See Screenshot: The open dialogue puts the buttons below the screen. Screen res is 1920x1200 but the app window is not maximized. Can be reproduced on laptop screens. | Jawahar | Closed
10 | General Improvements | 2013-12-29 | Doesn't remember the last path when "browsing for folder" | will be done | Jawahar | Closed
11 | General Improvements | 2013-12-29 | Settings and "about" buttons don't have any hover or mouse over effects |  | Marwin | Closed | mr: thanks!
12 | General Improvements | 2013-12-29 | The quality of the thumbnails is really bad, sadly. Please try to improve this as this will be extremely important for the application |  | Jawahar | Closed
13 | General Improvements | 2013-12-29 | We should call "delete directory" "remove from database". Otherwise people might be scared :-) |  | Jawahar | Closed | Label has changed. mr: a lot better, thanks!
14 | Usability and UI | 2013-12-29 | Long folder names can't be read. Scrolling them is not a nice alternative. What do you think of a) either making the folder pane resizable or b) putting the full path in a tooltip on mouse over? |  | Jawahar | Closed
15 | General Improvements | 2013-12-29 | Full view can't deal with long file names |  | Jawahar | Closed | Tooltip will be coming. Also we can resize the pane.
16 | Feature Request | 2013-12-29 | Moving between images in full view would be great (somewhat like picasa) so the user doesn't have to return to browse view in between seeing full-size images | Maybe also use arrow keys on keyboard (left, right) | Jawahar | Closed | Done
17 | Usability and UI | 2013-12-29 | The application window behaves differently when in full view than when in browse view. the window can be moved in full view so this leads to accidental minimizing / resizing |  | Jawahar | Closed
18 | Usability and UI | 2013-12-29 | No task bar icon – please provide an icon |  | Jawahar | Closed | @Jawahar: What size in pixels do you need for the icon? Make an .ico file containing multiple sizes. At a minimum, you should have the following sizes: 16x16, 32x32, 48x48, and 256x256 according to the Windows icon visual guidelines. Having a single .ico file will help Windows pick the best size and scale it appropriately depending on the situation (application icon, large taskbar, small taskbar, etc.)
19 | Functionality | 2013-12-29 | Can we add a menu item "powerpic tutorial" or "first steps..." where we display a local, static HTML page (possibly with a video)? The page and the video can be delivered by me. Also, can powerpic ask on first launch:"welcome to powerpic. Would you like to see a quick tutorial on how to use PowerPic now? | Menu Items for Help: -PowerPic Help -Getting Started -About -- OK | Marwin | Closed | Waiting for Marwin to give the content. Mr: will add an html page mr: update: will add an html page, maybe you can move all "help" htmls into a directory "help" within the application? Would that work? I will add a video file once the application is finished, so no need to wait. maybe we can link "getting started" to another html.
20 | Other | 2013-12-29 | Screen for "About" | Jawahar will align, Marwin needs to develop | Jawahar | Closed | mr: PPT with contents is emailed to Jawahar Jr: PPT not received. Can you please resend it. Mr: added to this file, see worksheet "About Screen" below
21 | Other | 2013-12-29 | We should agree on the contents of the "settings". What do you suggest? | – Yes we should have file type extensions to be scanned, window theme, clear all data, etc. Will send you a complete list ASAP. | Jawahar | Closed | mr: thanks!
22 | Usability and UI | 2013-12-29 | "Add directory" and "search" should not be together, as no path can be entered into the field | See screenshot | Jawahar | Closed
23 | Usability and UI | 2013-12-29 | How would we display "only favorites"? So far, we can only "add to favorites". Should we put a static, non-removable folder item "favorites" to the directory tree?-Yes that is possible. | Should we put a static, non-removable folder item "favorites" to the directory tree? | Jawahar | Closed | - Yes that is possible. Mr: fine!
24 | Other | 29.12.2013 24.02.2014 | -do images "remember" how often they've been exported? Is this stored in the database? This will be very important. | Add to metadata of images how often they have been used (that is exported, printed, emailed). That way, users can see which images are "most popular" even if they are not favorites | Jawahar | Closed | –Need more info on this. Mr: Has been explained in an email - do you need more details? Mr: as one can sort by popularity, this can be closed
25 | Other | 2013-12-29 | images can be added to the filmstrip area but can't be removed yet | Maybe add a little X on hover… but I'm sure you will have a great idea on how to do this :-) | Jawahar | Closed
26 | Other | 2013-12-29 | -images in filmstrip area can't be viewed in full |  | Jawahar | Closed
27 | Other | 2013-12-29 | -images can be added "in between" of other images in the filmstrip area but images can not be moved around or changed in position in the filmstrip | Pictures in the filmstrip need to be sorted. When exporting, the position should be in the filename (e. g. "01-car.jpg; 02-horse.jpg", etc | Jawahar | Closed | Preserve order option given in export dialog.
28 | Other | 2013-12-29 | -folders can't be removed from database yet (delete key without function, too). Before removal, the user should be asked |  | Jawahar | Closed | - Will be done.
29 | Other | 2013-12-29 | -folders can't be imported into powerpic on drag'n'drop yet (from explorer) |  | Jawahar | Closed | - Will be done.
30 | Other | 29.12.2013 20.01.2014 19.02.2014 | -images in full view can't be added to the filmstrip area yet |  | Marwin | Closed | Doesn't work adequately, re-checking mr: works now, thanks!
31 | Usability and UI | 2013-12-29 | Usability is in certain cases very different to windows standard. When in doubt, picasa is a good example – Need more info |  | Marwin | Closed | Will provide more examples
32 | Usability and UI | 2013-12-29 | Browser View / folders: Should we add a context menu per folder? | The items would be: -Select all -Open folder location -Properties --> would say 23 items, xxxx total file size -Remove from Database | Jawahar | Closed
33 | Usability and UI | 2013-12-29 | Browser View / folders: Display rectangles (optional?) | Picasa displays images as rectangles including screen resolution. I like our tiles very much, but pictures in landscape orientation are losing some detail to the left and to the right. Best solution: A choice in the settings if thumbs should be displayed rectangular or squared. The "filmstrip" area would then also have to display rectangular thumbs | Jawahar | Closed | Please verify mr: i like!
34 | Functionality | 2013-12-29 | "Reset Powerpic" should move into "Settings" |  | Jawahar | Closed |  | 11
35 | Functionality | 2013-12-29 | Do we have an option to cleanup the database? | The database would check if the images still exist on the hard drive and then remove all orphaned thumbs / directories (please verify) | Jawahar | Closed | mr: please also see new point further below, "rescan"
36 | Usability and UI | 2013-12-29 | For tablet compatibility, the app should also work with gestures | Display context menu on long tap? Open full view with zoom (two fingers), close full view with pinch, etc. | Jawahar | Closed | Doesn't have to be implemented right now, however please keep this in mind. XF: Long tap context menu has been done. Close full view on pich isnot possible. It will conflict with zoom gesture. | 31
37 | Bugs | 29.12.2013 19.02.2014 | App crashes on "Reset" | See video | Jawahar | Closed | mr: cant be reproduced, closed
38 | Other | 2013-12-29 | Contents for Splash Screen | Text needed | Marwin | Closed | Splash Screen: You can use the same contents as in the about screen
39 | Usability and UI | 2014-01-20 | "About" dialogue not centered to parent window | This only applies to the about button on the top right hand corner. When clicked in the HELP menu, the window is centered | Jawahar | Closed
40 | Bugs | 2014-02-04 | Adding multiple images to filmstrip doesnt work | Select several images with CTRL-key Drag them to filmstrip area Expected: all images are in the filmstrip Actual: Only one image is in the filmstrip | Jawahar | Closed | Holding CTRL key when start dragging mr: Re-opened: Dragging multiple objects in windows explorer and other applications works without CTRL key - CTRL is for selection only. Jr : This is issue with .NET Framework ListBox that we used to display images. This is logged here. http://connect.microsoft.com/VisualStudio/feedback/details/809192/. But working for a workaround on this. mr: Can you loop through the selected images, same as when multiple selected pictures are added via keyboard shortcut? mr: beautiful, thanks!
41 | Bugs | 2014-01-20 | Crash when empty filmstrip is double-clicked |  | Jawahar | Closed
42 | Other | 20.01.2014 24.02.2014 | Test environment available! | I have set up a physical box now running Win7 Home Premium, 64-Bit in German. You can reach it on teamviewer at: 763137521 The password is XAMLfactory2014 it's a little slow, but it's working ;-) | Jawahar | Open | Please verify mr: Test setup running again, same login data
43 | Functionality | 2014-01-20 | Tags cant be removed |  | Jawahar | Closed
44 | Usability and UI | 2014-01-20 | Adding tags: Tag is not added pressing the return key | 1) open an image into full view 2) click into the "tags" text field 3) enter something expected: RETURN key adds the tag, possibly focuses into the text field again actual: nothing happens | Jawahar | Closed
45 | Usability and UI | 2014-01-20 | Add a blank before each tag | Multiple tags are shown like this: one,two,three,four Better: One, two, three, four | Jawahar | Closed | now each tag listed in separate line to make deletion easier. Mr: cool! :-)
46 | Questions | 2014-01-20 | Where is the database stored? | If the application is packaged it may be important to be able to change the path to the database. Where is the database located currently? Can this be changed without having to rebuild the application? | Jawahar | Closed |  | 100
47 | Bugs | 2014-01-20 | Search only works once | 1) Browse view 2) Enter any search term, e. g. "blue" 3) results appear 4) Enter a new search term Expected: A new search is conducted Actual: Nothing happens | Jawahar | Closed
48 | Bugs | 2014-01-20 | Any search term returns "20" | 1) Enter anything 2) Even if no results are found, there is a "20" below the button "Back to library" | Jawahar | Closed
49 | Bugs | 2014-01-20 | Search for multiple tags has strange behaviour | 1) Enter "maple leaf" 2) no results are shown, only "20". 2b) there is another search term in the search input field | Jawahar | Closed
50 | Bugs | 2014-01-20 | "Add to favorite" button is active even if there are no search results | 1) Enter anything 2) Even if no results are found, there is a "Add to favorite" button and it's active | Jawahar | Closed
51 | General Improvements | 2014-01-20 | Rename "back to library" button to "back to results" in search results | 1) Browse view 2) Enter any search term, e. g. "blue" 3) results appear 4) Open any image 5) "Back to library" button returns to search results - which is great! - but the button says "Back to library" | Jawahar | Closed | Potential solution: Call the button "back to results" or just "return" if the name cannot be changed depending on the state
52 | Bugs | 2014-01-20 | Items in menu bar are different in browse view and in full view |  | Jawahar | Closed
53 | Bugs | 2014-01-20 | File->Exit without function [in full view] |  | Jawahar | Closed
54 | Feature Request | 2014-01-20 | Add a text description to images | Below the image and its meta data, add a block "Description". Text can appear below the headline, for example "A brown horse is eating an apple". | Jawahar | Closed | Please let me know how complicated / how much effort it would be for you to make the text description searchable.
55 | Bugs | 2014-01-20 | An old search term keeps appearing in full view | Search for something. Return to browse view. Delete the search term. Open any image to full view. An old search term appears in the text input in full view. | Jawahar | Closed
56 | Feature Request | 2014-01-20 | Add keyboard support to full view | Arrow keys should be usable to move between images. Escape returns to browse view. | Jawahar | Closed |  | 16
57 | Feature Request | 20.01.2014 19.02.2014 24.02.2014 | Add keyboard support to browse view / search | In Search results, pressing the escape key returns to browse view | Jawahar | Closed | mr: Re-opened: Doesn't work. 1) Open application 2) Enter any tag into the search input 3) see the results 4) Press Escape Expected: Return to browse view Actual: Nothing happens mr: Re-opened: Works, but does not work on first run of the application
58 | Feature Request | 2014-01-20 | Add keyboard support for adding images to filmstrip | 1) Select several images 2) Press CTRL-Enter to add the selected images to the filmstrip (no drag'n'drop needed) 3) The images are deselected afterwards | Jawahar | Closed | mr: VERY cool!
59 | General Improvements | 2014-01-20 | Improve Settings-window | Re-order items and rename one item | Jawahar | Closed
60 | Feature Request | 20.01.2014 19.02.2014 | Settings-Window: Above "select theme", add "select language" | - not necessary right now, but keep this in mind please :-) | Jawahar | Waiting | Localization may come at a later stage mr: How much effort would this be? Please estimate.
61 | Other | 2014-01-20 | Navigation / directories, subdirectories inconsistent | I don't like the navigation between directories and subdirectories; directories are empty but appear on the same level as subdirectories. I will re-check our emails on this and try to find a better solution. | Marwin | Closed |  | 95
62 | Usability and UI | 28.01.2014 04.02.2014 | [Settings] -Z-Index issue with "theme" dropdown |  | Jawahar | Closed | This issue was not produced. Please share the screen shot of this issue. Mr: Cant reproduce on current version -> closed
63 | Usability and UI | 2014-01-28 | [Full View] - images cant be added to filmstrip |  | Jawahar | Closed
64 | Questions | 2014-01-28 | Is it possible to add an option to "settings": Display tags in a separate pane (pane to the right)? That way, descriptions could be longer. If not checked, the tags would remain on the left and not appear in a new pane |  | Jawahar | Closed
65 | Questions | 2014-01-28 | Is it possible to add an option to settings to set the background color of the application ("Use white background color") ? | Your "theme" idea has been great! Maybe we can change the background color, too, without too much effort. White would look more "friendly". | Jawahar | Closed
66 | Usability and UI | 2014-01-28 | Full view: Descriptions: Adding a description doesn't wrap text |  | Jawahar | Closed
67 | Usability and UI | 2014-01-28 | [About window] -Clicking anywhere should close the window -Clicking Escape should close the window |  | Jawahar | Closed
68 | Usability and UI | 2014-01-28 | [Browse view] Graphical Element needed to increase the thumbnail size | what size is stored in the database? Smallest is perfect for browsing large collections, ca. 320px width would be better for a larger preview and 400-480px is perfect to see fine details. What do you recommend? The preview size should be changeable directly in browse view, not in settings. | Jawahar | Closed | mr: Great direction, needs some fine-tuning. Thank you, I like where this is going! | 105
69 | Usability and UI | 2014-01-28 | Use Touch gesture to increase thumbnail size (if possible) |  | Jawahar | Closed | XF:technically impossible, since listbox panning gesture will conflict. | 68 105
70 | Usability and UI | 2014-01-28 | "Add to Favorites" button appears on empty search results ("0 results found") |  | Jawahar | Closed
71 | Bugs | 2014-01-28 | Returning from an empty result set, the view is empty. One has to change folders to get back to seeing images |  | Jawahar | Closed
72 | Bugs | 2014-02-04 | Searching for multiple tags doesn't work (probably not implemented yet ;-) ) |  | Jawahar | Closed | It was implemented. Sepearte the search tags using , and try mr: Re-opened: Doesn't work: Searching for 2 tags will return "either" tag (OR), not "both" tags (AND). Best: Both, AND and OR. Google does AND searches with "+one +two", so maybe we can do it that way, too?
73 | Usability and UI | 2014-01-28 | Filmstrip gets a vertical scrollbar when containing many images, but images are only aligned horizontally. | Best: Images wrap to the visible area, vertically scrollable. -Filmstrip should be draggable upwards to maybe up to two rows of images and have minimum height of one row of images | Jawahar | Closed |  | 99
74 | Usability and UI | 2014-01-28 | An option [settings] to increase filmstrip thumb size to the minimum thumb size in browse view | Thumb size in filmstrip area very small; This looks good on smaller screens, but looks bad on larger screens. Maybe we can increase the thumbnail size in the filmstrip to the minimum size of the rest of the app and/or add an option to settings "use large preview thumbs in export area" or similar | Jawahar | Closed
75 | Functionality | 2014-01-28 | [Export] -Add date to default name, e. g. 20140129-export |  | Jawahar | Closed
76 | Bugs | 2014-01-28 | Non-existent images can be opened | 1) Open the application 2) Double-click the empty space 3) Something appears that shouldn't appear | Jawahar | Closed
77 | Bugs | 2014-01-28 | No sorting options on search results |  | Jawahar | Closed
78 | Usability and UI | 2014-02-04 | Add to Favorites via Drag'n'Drop | Adding to favorites would be a lot faster if it would work with Drag'n'drop from browse view, too | Jawahar | Closed | mr: GREAT! This is much faster now!
79 | Bugs | 04.02.2014 24.02.2014 | The same folder can be added twice |  | Jawahar | Closed | mr: Re-opened: If the folder is added and is added with the folder above, it can be added twice
80 | Usability and UI | 2014-02-04 | Remove "Reset Powerpic" from File Menu |  | Jawahar | Closed |  | 34
81 | Usability and UI | 04.02.2014 24.02.2014 | [Full view] Un-Focus "Tags" text input with Escape key | That way, one can return to browse view with keyboard only | Jawahar | Closed
82 | Usability and UI | 2014-02-04 | [Settings] Close Settings Window with Escape key (like About window) |  | Jawahar | Closed
83 | Questions | 2014-02-04 | Touch devices: How can one remove images from the filmstrip (no "hover" available) ? |  | Jawahar | Closed | xf: you can find the delete context menu for flimstrip items. This context menu opened on touch and hold. You can use this to remove images.
84 | Usability and UI | 2014-02-04 | [Full view] Clipping issue when resizing window in full view |  | Jawahar | Closed | Can you please provide screenshot for this issue? Mr: Please see worksheet 84 below
85 | Feature Request | 2014-02-04 | [Browse view] Add preview feature | When in browse view and small thumbnails are shown: Click and hold an image to display its large preview. -> That way, details can be seen better without having to go to "full view", which is slow on 24 megapixel images | Jawahar | Waiting | xf: Image rendering time will be same in both Full View and the Popup window (as you mentioned large preview). You really need this feature ? Mr: I understand… i thought a large preview would be a larger thumb, e. g. 480px and not the "full view" image. you can leave it out for now. | 68
86 | Usability and UI | 2014-02-04 | [Settings] Descriptions under labels are wrong | Thank you for moving the buttons. The descriptions also need to be exchanged, see screenshot | Jawahar | Closed
87 | Feature Request | 2014-02-04 | [Sorting] Also sort images by number of exports, "times used" or "times exported" |  | Jawahar | Closed | See scope extension email from January 24 mr: "Popularity" - great! | 24
88 | Usability and UI | 2014-02-04 | [Full view] Do you maybe have a royalty-free, more beautiful icon for "edit tags"? Just a normal pencil or like in IOS? |  | Jawahar | Closed | Image taken from the Metro Studio tool. Mr: a lot better, thank you
89 | Other | 2014-02-04 | Legal requirements | Do you have the license for the images available? Can you copy it somewhere in the app folder or email it to me? Germany is a very strict country when it comes to legal stuff :-/ Thank you! | Jawahar | Closed | All the images used in this project has been taken from the Metro Studio tool. This tool provides royalty free images. For more info look into the following link. http://www.syncfusion.com/downloads/metrostudio mr: will check, thank you
90 | Questions | 2014-02-04 | Do you have experience with bug tracking tools? Can you recommend something? Excel is tedious ;-) | Once we are finished with this project, we will add some bug tracking platform to improve future collaboration | Jawahar | Working / Investigating | Sure
91 | Feature Request | 2014-02-19 | Add keyboard support to browse view / search | In browse view and with search results, navigate results with arrow keys (already implemented). OPEN an image with spacebar or return key | Jawahar | Closed
92 | Feature Request | 19.02.2014 24.02.2014 | Add keyboard support to browse view / search | Shortcut to focus on search input, maybe CTRL-F or F3. Escape will unfocus and set the focus back to the main window / browse area, so the user can continue navigating with arrow keys | Jawahar | Closed | mr: Re-opened: Doesn't work on launch of the application. Works only after an album has been selected. Should also work in full view
93 | Feature Request | 2014-02-19 | Add keyboard support to browse view | Shortcut to move a folder up, move a folder down - maybe something like ALT-PgUp, ALT-PgDown. The focus then switches back to the browse area, so the user can continue navigating with arrow keys | Jawahar | Closed | mr: you´re free to use shortcuts you find more useful. Xf: use shift+up, shift+down
94 | Feature Request | 2014-02-19 | Add keyboard support to full view | Shortcut CTRL-Enter to Add full-view image to filmstrip (same as in browse view) | Jawahar | Closed |  | 58
95 | General Improvements | 2014-02-24 | Folder navigation / representation | The problem with the flat structure is that empty directories get displayed, too. My suggestion would be to simply not display empty directories but other than that keep it the way it is. What do you think? | Jawahar | Closed | Jawahar recommended: "I Iike the way Picasa showing the flat folder structure. If you add a folder into Picasa, the root folder and all the sub folders will add in flat structure and sorted by date. This would be easy for maintenance and querying, whereas folder tree is a hectic for database. Also the folder can added from various source and can be grouped as below image."
96 | General Improvements | 2014-02-24 | Close "search options" window with Escape key |  | Jawahar | Closed
97 | Bugs | 2014-02-24 | Context menu appears on "favorites" folder, leading to a couple of errors | "Favorites" can be deleted, etc. - the app keeps crashing | Jawahar | Closed | Now only 'Select All' menus show for Favourite folder
98 | Feature Request | 2014-02-24 | Drop "Print" button and add "Slideshow" button instead | As the print button is without function and I actually never print pictures, why not add a button for the slideshow instead? | Jawahar | Closed | Marwin wrote on Jan. 24 (see next worksheet): "D) Slideshow: View images in filmstrip in full-screen (everything else goes black), a click or arrow keys move to the next image, escape key returns to standard view"
99 | Usability and UI | 2014-02-24 | Filmstrip: Line up images in rows | It's great the filmstrip is resizable now. The images should line up in rows. When resized, the images should be added in other rows. That way, the scrollbar then should be vertical only - see illustration in worksheet 99 | Jawahar | Waiting | xf: this have techninical difficulty on changing the orientation of items on resizing. We will analyze further and let you know the posibility. Mr: great, thanks.
100 | Questions | 2014-02-24 | Where is the default path for the database stored? | Is it coded within the application or does it come from any INI file within the app directory? The latter would be better | Jawahar | Closed | We can change the default path in Settings Window | 46
101 | Usability and UI | 2014-02-24 | [About window] -Clicking anywhere should close the window |  | Jawahar | Closed |  | 67
102 | Usability and UI | 2014-02-24 | [Browse view] Scroll to position / Keep focus | 1) Open a folder with many images 2) Scroll down 3) Open an image somewhere in the middle 4) ESCape to return to browse view -> The view is set to the beginning of the folder. Better: the view scrolls to the last image added; the last image added is still focused (blue bracket). If one navigates in full view with arrow key and returns to browse view, the image last displayed should be focused. | Jawahar | Closed
103 | Feature Request | 2014-02-24 | Add tags to multiple images at once | [Browse view] 1) Select several images with the CTRL key 2) Add tags that are valid for all selected images via contect menu or menu item, whatever seems more usable Alternatively: Add to context menu on folder: "Tag images…", but less cool ;-) | Jawahar | Waiting | Please calculate and tell me how much it would cost
104 | Bugs | 2014-02-24 | Crash on empty search | 1) Open application 2) Enter search field 3) Just press enter, without entering anything 4) Application crashes | Jawahar | Closed
105 | Bugs | 2014-02-24 | Zoom slider "forgets" setting when changing the folder | 1) Select any folder 2) Increase size with zoom control 3) change folder 4) the zoom slider is still set to "zoom", but the thumbnails appear in small | Jawahar | Closed
107 | Questions | 2014-02-24 | Internal: Thumbnail storage; file type | Currently, the internal thumbs seem to be stored as JPGs. Would PNGs be smaller (and less artefacts, better quality)? Would it be complicated to try out? | Jawahar | Closed | Just an idea.. Let me know if it´s worth trying or if we rather leave everything as it is. Xf: JPEG is better than PNG for best size.
108 | Usability and UI | 2014-02-24 | [Full view] / Image meta data: Display how often an image has been exported | Now that the information is available, we should display it somewhere - maybe right above, behind or below the file size. Example: "2.0 MB ¦ 99x used" | Jawahar | Closed
109 | Bugs | 2014-02-24 | [Sorting] The control only works when the text label is clicked, not when the radio button next to it is clicked |  | Jawahar | Closed
110 | Usability and UI | 2014-02-24 | [Browse view] Add keyboard shortcut to zoom slider | Maybe alt-1, alt-2, alt-3 for preview sizes? | Jawahar | Closed
111 | Bugs | 2014-02-24 | [Sorting] Strange behavior sorting by size | Sorting by size doesn't work. | Jawahar | Closed
112 | Bugs | 2014-02-24 | [Sorting] Returning from Full view should remember sorting and thumbnail size | Should work in favorites, too | Jawahar | Closed |  | 105 102

## Lookup (hidden)
Status
Open
Working / Investigating
Waiting
Closed
Categories
Bugs
General Improvements
Performance Improvements
Questions
Other
Feature Request
Usability and UI
Functionality

## Scope 24.01.14
Copy of our email traffic
Hi Jawahar,
thanks again for our conversation this afternoon. I'm glad you raised your concerns - please feel free to contact me anytime in case anything comes up.
I do agree to pay an additional $200, but please let us agree on features first.
Must have features:
1) Search for multiple tags (horse, brown)
2) Description, search in description and/or tags and/or other data (see drawing - just an example, feel free to modify)
3) Improved export dialog: open a dialogue, ask for target resolution for images, optionally enter a name for the collection (see below, nice to have "C")
4) improved folder navigation, i need to figure something out.
5) Remove single tags, remove all tags per image
6) Favorites
7a) Store how often an image has been exported, so one can sort (see next point)
7b) Sort images in browse view, in search results (file name, creation date, number of exports, rating)
8) touch / gesture navigation: scroll, zoom in, zoom out, etc. - it must be cool!! ;-)
9) Store larger versions of the image in the database as "big preview", 1024x768 resolution or similar. This should speed up previewing very large (24MP) images on slow machines!
Nice to have features:
A) rate images in stars (1 to 5). Optionally, this can also be done on the keyboard by pressing ALT-1 to 5. Maybe one can even select a number of images in browse view, press ALT-1 to 5, all selected images get the rating after a prompt ("Do you want to rate the selected images with 3 stars?")
B) Make filmstrip area resizable (draw upwards ; reset view to standard) - that way, one could create and preview a larger collection of files to be exported
C) Album History / export log table: Which combination of images have been exported when - open, modify collections from the past (e. g. "Spring Catalogue 2014"). Of course, old albums / log entries can be deleted for good. The log can be opened via the file menu ("Export History"). It can be a simple table (Date, name of collection, number of images, potentially a text search input. The view must be scrollable)
D) Slideshow: View images in filmstrip in full-screen (everything else goes black), a click or arrow keys move to the next image, escape key returns to standard view
Very optional for now:
E) tag cloud: most frequently used tags (see scope document)
F) Import, Backup database - not necessary right now, but keep this in mind - everybody fears crashing disks :-)
G) Localization: Select app language
--> Please let me know if this is doable and/or if there is anything else you need. You have been doing a very good job and I want you to remain happy.
Also, please let me know anytime if you need anything just as you did today. We might have more coming up in the future ;-)
I'm looking forward to receiving your suggested milestone plan. Thank you so much!
Best regards and have a great day,
Marwin
Note on A32: Marwin: Please see Issue item #95
Note on A42: Marwin: Low Priority
Note on A45: Marwin: See item #98

## About Screen
Thank you for using our product. We hope you find this software as useful as we do. Are there any features missing? Is there anything else you would like to see? Please let us know at: feedback@symposity.com

## 84
Clipping issue
1) Application not maximized, an image is opened
2) Application now maximized, clipping error in display

## 99
Please align images horizontally, add scrollbar vertically. You can also increase the maximum vertical size of the filmstrip (max resizable height).